## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
login-page
| Table 1 | login-page
Active Cases
| Table 1 | Active Cases
admin-Manage User
| Table 1 | admin-Manage User
Change Password
| Table 1 | Change Password
logout
| Table 1 | logout

## login-page
Test Case Project |  | Student Score Visualization Tool | Test Case Description | Verifying secure login process for all user roles (student, educator, admin)
Created By |  | Amarnath Reddy N | Reviewed By | Penumetsa Abhiram Varma | Version |  | 1.0
QA Tester’s Log |  | Review login functionality for role-based access, validate JWT auth from SDD
Tester's Name |  | Jaya Siddu Karthikeya | Date Tested | 2025-05-07 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Secure login and redirection to respective dashboards
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Navigate to http://localhost:3001/login |  | Login page loads with student/educator/admin login input fields | Login page loads with input fields for email and password |  | Pass
2 | Enter valid credentials for student |  | JWT token generated, user authenticated, redirected to StudentDashboard (from Login.js) | JWT issued, user redirected to /student/dashboard as per AuthContext |  | Pass
3 | Enter valid credentials for educator |  | JWT generated, redirected to EducatorDashboard (from EducatorDashboard.js) | JWT issued, user redirected to /educator/dashboard |  | Pass
4 | Enter valid credentials for admin |  | JWT generated, redirected to AdminDashboard (from AdminDashboard.js) | JWT issued, user redirected to /admin/dashboard |  | Pass
Dialogue box for forgot password
5 | Enter incorrect credentials |  | Error message “Invalid credentials” shown (from AuthenticationException in SDD §6) | Error handled via AuthenticationException; message appears on login form |  | Pass
6 | Submit with empty fields |  | Validation error: “Please enter email and password” | Frontend shows MUI alert message from Login.js validation logic |  | Pass
Support

## Active Cases
Test Case Project |  | Student Score Visualization Tool | Test Case Description | Verify charts and statistics load correctly on student dashboard
Created By |  | Amarnath Reddy N | Reviewed By | Penumetsa Abhiram Varma | Version |  | 1.0
QA Tester’s Log |  | Validate performance trends, score listings, batch comparison visualizations
Tester's Name |  | Suprith Reddy | Date Tested | 2025-05-07 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Dashboard components render and load personal and comparative data correctly
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Log in as student and go to Dashboard |  | StudentDashboard.js loads with name, department, academic year, etc. | Dashboard loads successfully. Student info (name, roll no, dept) fetched via API and displayed |  | Pass
2 | Navigate to “Performance Trends” tab |  | Line charts and bar charts should render showing semester-wise performance | Recharts LineChart and BarChart render semester GPA trends correctly using scores.js data |  | Pass
3 | Click on “View Scores” |  | Table or list of all personal scores is displayed | Subject-wise scores loaded via Score API and rendered using table component |  | Pass
4 | Navigate to “Batch Comparison” section |  | Batch averages are shown alongside student scores | Comparative analytics chart renders with anonymized batch averages using Analytics API |  | Pass
5 | Change semester filter |  | Display updates dynamically for selected semester | Recharts components re-render based on filtered semester. Scores API called with new semester param |  | Pass

## admin-Manage User
Test Case Project |  | Student Score Visualization Tool | Test Case Description | Test admin’s ability to manage user accounts and roles
Created By |  | Amarnath Reddy N | Reviewed By | Penumetsa Abhiram Varma | Version |  | 1.0
QA Tester’s Log |  | Verifying admin functions: create, edit, and assign user roles
Tester's Name |  | Jaya Siddu Karthikeya | Date Tested | 2025-05-07 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Ensure admin can manage users via AdminDashboard.js and Role APIs
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Login as admin and navigate to “User Management” page |  | AdminDashboard.js loads with user management options | Admin successfully logs in; “User Management” section visible |  | Pass
2 | View list of users with roles and status |  | User list table with columns: name, email, role, status | Fetched from GET /api/users. Table rendered with pagination |  | Pass
Add User
3 | Click “Add User” and enter name, email, role, and password |  | Form accepts input and submits via User API | User created successfully via POST /api/users. Role saved in MongoDB |  | Pass
4 | Try adding user with missing mandatory fields |  | Validation error displayed | Frontend blocks submission, shows required field warnings |  | Pass
5
6
7
8
Edit User
11 | Edit an existing user’s role (e.g., change student to educator) |  | Role updated and saved | PUT request updates user role. Role change reflected on next login |  | Pass
12 | Attempt to delete a user |  | Confirmation dialog shows, user removed from DB | User removed via DELETE /api/users/:id. User no longer listed |  | Pass
13
14
15
16

## Change Password
Test Case Project |  |  | Test Case Description
Created By |  |  | Reviewed By |  | Version |  | 1.0
QA Tester’s Log |  | Review comments in version 1.0
Tester's Name |  |  | Date Tested |  | Test Case (Pass/Fail/Not Executed)
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1
2
3
4

## logout
Test Case Project |  | Student Score Visualization Tool | Test Case Description | Validate logout action clears JWT session and redirects to login
Created By |  | Amarnath Reddy N | Reviewed By | Penumetsa Abhiram Varma | Version |  | 1.0
QA Tester’s Log |  | Ensure session is terminated and access to protected routes is revoked
Tester's Name |  | Suprith Reddy | Date Tested | 2025-05-07 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Logout should remove session and deny access to protected pages
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Click on logout icon from dashboard |  | JWT cleared from local storage, AuthContext reset | Logout button in Navbar.js triggers AuthContext logout function. JWT removed from localStorage |  | Pass
2 | User is redirected to login page |  | Login form displayed | Redirect successful. Login.js rendered again showing email/password fields |  | Pass
3 | Attempt to access dashboard via URL |  | “Unauthorized” error or redirect to login | Attempting /student/dashboard after logout triggers AuthorizationException and redirects to login |  | Pass